## Tasks
Task Name | Assigned To | Labels
BUG_Admin panel_User_BUG_015_Email ID Field | Sarvanaraj P;Barath Kaileash G.V;Prakash Raj S | Admin Panel Bugs;Re-Opened Bugs;Minor
Bug_Creator_Home_BUG_008_Post job now is working without entering details | Gayathri Bandhila | User Panel Bugs;Minor;Verified Bugs
Bug_Financials_Withdraw_BUG_012_“View Transactions” incorrectly redirects to the Creator Financials module | Aravind Sunkara;Sarvanaraj P;Prakash Raj S;Deepak Rajan | User Panel Bugs;Re-Opened Bugs;Major
Bug_ Creator My Profile _ After clicking Unread message in notification page, its not move to read | Sarvanaraj P;ayyappa tellamekala;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;New Bugs;Major
Bug_Admin Subscription_BUG_001_The Name field accepts only alphabetic characters and rejects any numeric input. | Aravind Sunkara;Sarvanaraj P;Prakash Raj S | Admin Panel Bugs;Verified Bugs;Critical
Bug-Homepage - Bug-005Clicking on Content Creator Functionality Not redirecting to Content Creator page | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S;Nala Sravan Kumar | User Panel Bugs;Re-Opened Bugs;Verified Bugs
Task_003-Test My project -Hire freelancers functionalities | Barath Kaileash G.V | Task
Suggestion_User panel(collaborator) _ Project duration stand and end date should be shown | Sarvanaraj P;Barath Kaileash G.V;Prakash Raj S | Suggestion
Smoke Test_Build Version: 1.0.0_Admin_User | Barath Kaileash G.V | Smoke Test
Bug_Admin_ Login _Bug-005 Remember me functionality is not working for password | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | Admin Panel Bugs;Verified Bugs
Bug-Admin-Bug-ID-019-Verify Template button functionality
BUG_UserPanel_Collaborators_Homepage - Unable to like a job in Best match | Sarvanaraj P;Jagadeesh kalyan;Prakash Raj S;Vijay Kumar N | User Panel Bugs;Re-Opened Bugs;Major
Bug_Admin_Login_Bug_004 Email Not accepting in upper case functionality | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | Admin Panel Bugs;Verified Bugs;Critical
BUG_Mobile_testing_HomePage- pop-up message repeating | Sarvanaraj P;Prakash Raj S;Vijay Kumar N | User Panel Bugs;New Bugs;Minor
BUG_creator_Financials_Add funds_BUG_008_Card number not working | Sarvanaraj P;Barath Kaileash G.V;Prakash Raj S;Deepak Rajan | User Panel Bugs;Verified Bugs
BUG_UserPanel_HomePage - Both in creator and Collaborator unable to review | Sarvanaraj P;Prakash Raj S;Vijay Kumar N | User Panel Bugs;New Bugs;Minor
Bug_Creator_Home_BUG_021_Resend otp button is not working as expected for email | Gayathri Bandhila | User Panel Bugs;Minor;Verified Bugs
Bug_Creator_Home_BUG_046_After clicking View all button Cancelled spelling appearing incorrect | Sarvanaraj P;Gayathri Bandhila;Prakash Raj S | User Panel Bugs;Re-Opened Bugs;Minor
Bug_ Collaborator My Profile _Bug 50_ Unread message count badge has to display on message icon when receiving new messages | Sarvanaraj P;Kolimi Shaik Fazil;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
Bug_ Creator My Profile _Bug_018_ After clicking Audio call button, call not connect to other user and error displayed | Sarvanaraj P;ayyappa tellamekala;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;Re-Opened Bugs;Major
Bug_Creator-Subscription_BUG_007_After clicking Subscribe to Pro button payment details are saved but confirmation message not displayed | Sarvanaraj P;Kolimi Shaik Fazil;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
Bug_ Creator My Profile _Bug 20_ After clicking "away" option, user Status did not update properly across application | Sarvanaraj P;Kolimi Shaik Fazil;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;New Bugs;Major
BUG_Admin_Settings page-Show password (Eye button) is not present | Sarvanaraj P;Prakash Raj S;Vijay Kumar N | Admin Panel Bugs;Re-Opened Bugs;Minor
Bug_ Creator My Profile _Bug_010_ System accepts pdf file and profile image not displayed properly | Sarvanaraj P;ayyappa tellamekala;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;Re-Opened Bugs;Minor
Bug_Admin _Notifications_Bug_008 Notifications are not displayed | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | Admin Panel Bugs;Verified Bugs;Major
Bug_Admin_Notifications Bug-009 Notifications are Disabled | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | Admin Panel Bugs;Minor;Verified Bugs
Task_003-Test Collaborator Profile, Message and Notification Section | ayyappa tellamekala | Task
Bug Subscription-Collaborator Page_BUG_004_ The pricing unit for the Agent Plan | Aravind Sunkara;Sarvanaraj P;Kolimi Shaik Fazil;Prakash Raj S | User Panel Bugs;Verified Bugs;Critical
BUG_Admin_Settings page- Unable to fill Role | Sarvanaraj P;Prakash Raj S;Vijay Kumar N | Admin Panel Bugs;Verified Bugs
Bug_Financials_Withdraw_BUG_004_Attempt to withdraw an amount greater than the available account balance. | Aravind Sunkara;Sarvanaraj P;Prakash Raj S;Deepak Rajan | User Panel Bugs;Verified Bugs;Major
Bug_Creator-Subscription_BUG_001_The Subscribe to base plan button is not working in monthly plan | Sarvanaraj P;Kolimi Shaik Fazil;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;Re-Opened Bugs;Major
BUG_UserPanel_Creators_Homepage - Alignment issue in View all jobs | Sarvanaraj P;Prakash Raj S;Akash Barik;Vijay Kumar N | User Panel Bugs;Re-Opened Bugs;Minor
Bug_ Creator My Profile _Bug 30_ Timer is not updating and remains stuck at initial value when click on resend OTP button | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;New Bugs;Minor
Smoke Test_Build Version:1.0.2_Join as a creator, my project & Financials | Barath Kaileash G.V | Smoke Test
Bug_ Collaborator My Profile _Bug_015_ Notification is clickable but no action happens | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Minor;Verified Bugs
Bug_Creator_Find collaborator_Find collaborator button_BUG_002_Find collaborator button is not working | Gayathri Bandhila | User Panel Bugs;Minor;Verified Bugs
BUG_Creatot_Financials_BUG_004_Amount field increase and decrease of the amount is been adjusted by the mouse | Sarvanaraj P;Barath Kaileash G.V;Prakash Raj S;Deepak Rajan | User Panel Bugs;Verified Bugs
BUG_Creator_My project_BUG_014_Awaiting contracts | Sarvanaraj P | User Panel Bugs;Critical
Smoke Test Build Version :1.0.3_Admin Dashboard | Gayathri Bandhila | Smoke Test
Bug_ Collaborator My Profile _Bug_024_ After saving , location data not displayed | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Minor;Verified Bugs
Bug_ Collaborator My Profile _Bug_013_ System did not shows Error message " Please fill out this field" | ayyappa tellamekala | User Panel Bugs;Minor;Verified Bugs
Bug_ Creator My Profile _Bug_016_ After clicking save button, the system is still saved even through all fields empty. No validation error appear | ayyappa tellamekala | User Panel Bugs;Verified Bugs;Major
Smoke Test Build Version: 1.0.1_Admin_Subscription | Aravind Sunkara | Smoke Test
Smoke Test_Build Version: 1.0.3_Admin_User | Barath Kaileash G.V | Smoke Test
Bug_Creator-Subscription_BUG_010_The pricing unit for pro plan | Sarvanaraj P;Kolimi Shaik Fazil;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;Re-Opened Bugs;Major
Bug_Creator_Home_BUG_024_Cancelled tab is not working | Gayathri Bandhila | User Panel Bugs;Minor;Verified Bugs
BUG_Admin Panel_User_BUG_002_Active box | Barath Kaileash G.V | Verified Bugs
Bug_ Collaborator My Profile _Bug 57_ System accepts 10MB image file, and the profile image uploaded without any errors | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;New Bugs;Major
Bug_ Creator My Profile _Bug_019_ After clicking video call button, call not connect to other user and error displayed | Sarvanaraj P;ayyappa tellamekala;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;Re-Opened Bugs;Major
BUG_Admin panel_User_BUG_004_Search bar | Barath Kaileash G.V
BUG Join as Collaborator Profile Page Function - Tab key shifting options | Vijay Kumar N | User Panel Bugs;Verified Bugs
Bug_ Collaborator My Profile _Bug_016_ After clicking on the read notification , the entire notification page closes and no further action occurs | ayyappa tellamekala | User Panel Bugs;Minor;Verified Bugs
Bug_Admin Subscription_BUG_005_The Discount field accepts only alphabetic characters and numeric valves and rejects any Special characters | Aravind Sunkara;Sarvanaraj P;Prakash Raj S;Nala Sravan Kumar | Admin Panel Bugs;Minor;Verified Bugs
Smoke Test Build Version :1.0.1_Admin Dashboard | Gayathri Bandhila | Admin Panel Bugs;Smoke Test
Suggestion_User panel (Creator)_By clicking the step button it should show the sign up page | Sarvanaraj P;Barath Kaileash G.V;Prakash Raj S | Suggestion
BUG_mobile_testing_My_Profile page- UI Design issue in Add portfolio | Sarvanaraj P;Prakash Raj S;Akash Barik;Nala Sravan Kumar;Vijay Kumar N | User Panel Bugs;Re-Opened Bugs;Minor
Bug_ Collaborator My Profile _Bug_020_ After saving, when followers count is zero, it doe not appear on profile page. Once follower count increased to one , after saving the profile displayed "follower=1" | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Minor;Verified Bugs
BUG_Admin_Settings page- When Page is refresh landing module | Sarvanaraj P;Prakash Raj S;Akash Barik;Vijay Kumar N | Admin Panel Bugs;New Bugs;Verified Bugs
Bug_ Collaborator My Profile _Bug_021_ After saving, The follower count still shows the manually updated value, instead of remaing zer | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Re-Opened Bugs;Minor
Bug-Beforesignup -Bug-005_Continue with Privacy Use Not redirecting to respective page | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
Smoke Test_ Build Version:1.0.4_Creator Subscription and Creator and Collaborator My Profile, Message & Notification | ayyappa tellamekala | Smoke Test
BUG_UserPanel_Homepage_Job search - Alignment and button faulty for filter section | Sarvanaraj P;Prakash Raj S;Akash Barik;Vijay Kumar N | User Panel Bugs;New Bugs;Major
Bug_ Collaborator My Profile _Bug_036_ After clicking audio call button, call not connect to other user and error displayed | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Re-Opened Bugs;Major
Task_004-Test Financials -Add funds functionalities | Barath Kaileash G.V;M Hariharasubramani | Task
Bug_ Creator My Profile _Bug 22_ The pop-ups did not displayed on phone verification page and instead appeared in profile page | Sarvanaraj P;ayyappa tellamekala;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
Smoke Test_Build Version:1.0.3_Admin_Panel_Settings_module | Vijay Kumar N | Smoke Test
Bug_Admin_Notifications Bug-011 Notifications not generating when user edits | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | Admin Panel Bugs;Verified Bugs;Major
Smoke Test Build Version: 1.0.4_Admin_Subscription | Aravind Sunkara | Smoke Test
Bug_ Creator My Profile _Bug_013_ After clicking save , System accepted numeric values in all fields without displaying any validation error | ayyappa tellamekala | User Panel Bugs;Minor;Verified Bugs
BUG_Admin panel_User_BUD_001_All User | Barath Kaileash G.V
Smoke Test_Build Version: 1.0.1_Admin_User | Barath Kaileash G.V | Smoke Test
Bug_ Collaborator My Profile _Bug 48_ The experience field not accepting numbers after entering numbers it displayed validation like "Only alphabets and spaces are allowed" | Sarvanaraj P;ayyappa tellamekala;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
Bug-Homepage Footer-Bug-021 Footer-Verify “Assign a Complete Project” navigation | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
BUG_Admin panel_User_BUG_010_Active status | Barath Kaileash G.V | Verified Bugs
Bug-signup - Check Weather Mutliple (@@) symbols Pop up dispalys | Mahesh Reddy Paduru | User Panel Bugs;Verified Bugs;Major
BUG_Admin_Settings page- Unable to Delete account | Sarvanaraj P;Prakash Raj S;Vijay Kumar N | Admin Panel Bugs;Verified Bugs
Bug_ Collaborator My Profile _Bug_040_ System accepts invalid inputs and allowed submission | Sarvanaraj P;Kolimi Shaik Fazil;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;Verified Bugs;Major
Bug_ Collaborator My Profile _ After clicking "away" option, user Status did not update properly across application | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;New Bugs;Minor
Bug-Footer Homepage Mobile Version-Bug-033-Verify “Assign a Complete Project” Text Overflow | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | User Panel Bugs;Re-Opened Bugs;Minor
Bug_Creator-Subscription_BUG_006_Cardholder name field accepts invalid input(like numbers and special characters) | Sarvanaraj P;Kolimi Shaik Fazil;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;Re-Opened Bugs;Minor
Smoke Test Build Version: 1.0.2_Admin_Analytics & Revenue splits | ayyappa tellamekala | Smoke Test
Bug_Creator-Subscription_BUG_011_The pricing unit for Agent plan | Sarvanaraj P;Kolimi Shaik Fazil;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;Re-Opened Bugs;Major
Task_006-Test Login functionalities | Mahesh Reddy Paduru | Task
Bug_Creator_Home_BUG_041_Numbers and special characters are accepting in location field in filter | Sarvanaraj P;Gayathri Bandhila;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
Bug_Creator_Home_BUG_030_State field accepts numbers and special characters | Gayathri Bandhila | User Panel Bugs;Minor;Verified Bugs
BUG_UserPanel_MyWorks page - Duration is not specified in Invited job | Sarvanaraj P;Prakash Raj S;Vijay Kumar N | User Panel Bugs;Re-Opened Bugs;Minor
Smoke -Test Build Version:1.0.4_ Signup and Login | Mahesh Reddy Paduru
Bug_ Collaborator My Profile _Bug 53_ The system accepts numbers in badge field, displayed validation that only alphabets and spaces are allowed | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;New Bugs;Minor
BUG_ mobile testing_ Creator My Profile _ Header, profile text, notification and messages are overlapping when scrolling in mobile view | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Akash Barik | User Panel Bugs;New Bugs;Major
Bug_ Collaborator My Profile _Bug_029_ After clicking save skill did not added to the list in edit skill section , but pop-up is showing | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Minor;Verified Bugs
Suggestion-User Pannel-Verify text on the Landing Page is clear and easily readable, whereas the text on the Before Signup and Login pages is not clearly readable. | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | Suggestion
Bug_ Creator My Profile _Bug_009_ System not displayed the correct image of the user in chat section | Sarvanaraj P;ayyappa tellamekala;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
Bug_Financials_Withdraw _BUG_002_IFSC Code field allows more than 11 digits. | Aravind Sunkara;Rajesh T;Sarvanaraj P;Prakash Raj S;Deepak Rajan | User Panel Bugs;Re-Opened Bugs;Major
BUG_Admin Panel_User_BUG_019_Full name is missing in the user management list | Sarvanaraj P;Barath Kaileash G.V;Prakash Raj S | Admin Panel Bugs;Verified Bugs
Bug_ Collaborator My Profile _Bug_037_ After clicking video call button, call not connect to other user and error displayed | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Re-Opened Bugs;Major
Task_003-Test Find Collaborator Page Functionalities | Gayathri Bandhila | Task
Bug_ Creator My Profile _Bug 31_ Verify email verification accepts only registered email | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;New Bugs;Minor
Task_002-Test Collaborator- Home Page Functionalities | Vijay Kumar N | Task
BUG_UserPanel_MyProfile page- Comma should used as a separator in skills | Sarvanaraj P;Prakash Raj S;Nala Sravan Kumar;Vijay Kumar N | User Panel Bugs;Verified Bugs
Bug_ Collaborator My Profile _Bug_017_ After clicking save button the Social link URL missing in profile page | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Minor;Verified Bugs
Bug_ Admin_ Analytics& revenue splits_BUG_004_The arrows clickable, but no sliding occurs; the sections do not change | Sarvanaraj P;ayyappa tellamekala;Jagadeesh kalyan;Prakash Raj S | Admin Panel Bugs;Re-Opened Bugs;Minor
Bug_Admin_Dashboard_BUG_004_Total revenue data is not found | Sarvanaraj P;Gayathri Bandhila;Prakash Raj S;Deepak Rajan | Admin Panel Bugs;Minor;Verified Bugs
Bug_Admin_Dashboard_BUG_007_Weekly revenue data is not found | Sarvanaraj P;Gayathri Bandhila;Prakash Raj S;Deepak Rajan | Admin Panel Bugs;Minor;Verified Bugs
Bug_Creator_Home_BUG_017_Skills in job list is disappearing when we click on it | Sarvanaraj P;Gayathri Bandhila;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;Verified Bugs;Major
Smoke Test Build Version: 1.0.2_Admin_Subscription | Aravind Sunkara | Smoke Test
Bug_Creator_ Find Collaborator_Search _BUG_001_Search button is not working | Gayathri Bandhila | User Panel Bugs;Minor;Verified Bugs
Bug_Admin_Dashboard_BUG_002_Active projects are not showing correctly | Sarvanaraj P;Gayathri Bandhila;Prakash Raj S;Deepak Rajan | Admin Panel Bugs;Minor;Verified Bugs
Suggestion_User panel(Creator)_Time duration should be kept for the project deadline | Sarvanaraj P;Barath Kaileash G.V;Prakash Raj S | Suggestion
Bug_Creator_Home_BUG_003_Not able to check posted job | Sarvanaraj P;Gayathri Bandhila;Prakash Raj S;Nala Sravan Kumar | User Panel Bugs;Minor;Verified Bugs
Suggestion_Admin Panel_Subscription _Search bar required for Subscription History | Aravind Sunkara;Sarvanaraj P;Prakash Raj S | Suggestion;Admin Panel Bugs;Major
Bug_ Creator My Profile _Bug 26_ Verify back button navigation from phone OTP verification screen | Sarvanaraj P;Kolimi Shaik Fazil;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;New Bugs;Minor
Task_001-Test My Project -All Contracts functionalities | Barath Kaileash G.V | Task
Bug_Admin_Dashboard_BUG_008_Not able to check project status | Gayathri Bandhila | Admin Panel Bugs;Minor;Verified Bugs
Bug_ Admin _Analytics& revenue splits_BUG_009_ When clicking on the Total subscription box, no action or response occur, even through value is visible | Sarvanaraj P;ayyappa tellamekala;Jagadeesh kalyan;Prakash Raj S | Admin Panel Bugs;Minor;Verified Bugs
Bug_Creator_Home_BUG_038_Added skills are disappearing in the complete profile | Gayathri Bandhila | User Panel Bugs;Minor;Verified Bugs
Bug_Admin Dashboard_BUG_013_Month option data is not there in project status | Gayathri Bandhila | Admin Panel Bugs;Minor;Verified Bugs
Suggestion_User panel (Creator)_By clicking the sign up button in the log in page it should show the main sign up page | Sarvanaraj P;Barath Kaileash G.V;Prakash Raj S | Suggestion
BUG Test Collaborator Home page Functionalities - Heart icon in saved jobs | Vijay Kumar N | User Panel Bugs;Verified Bugs
Smoke Test_Build Version:1.0.2_Admin_Panel_Settings_module | Vijay Kumar N | Smoke Test
BUG_Creator My profile_Creator profile details_BUG_002_Creator profile details not their when we retained back | Sarvanaraj P;Gayathri Bandhila;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
Bug_ Collaborator My Profile _Bug_039_ the Notification message does not navigate to a detailed view. | ayyappa tellamekala | User Panel Bugs;Minor;Verified Bugs
Bug_ Collaborator My Profile _Bug_033_ " Email verified successfully" Pop-up message not displayed | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Minor;Verified Bugs
BUG Admin dashboard Settings page functionalities - Profile picture update | Vijay Kumar N | Admin Panel Bugs;Verified Bugs
Bug-Homepage-Bug-004Clicking on Graphic Designer functionality not redirecting to designer page | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | User Panel Bugs;Re-Opened Bugs;Verified Bugs
Bug_Admin_Dashboard_BUG_011_yesterday option data is not there in project status | Gayathri Bandhila | Admin Panel Bugs;Minor;Verified Bugs
BUG_UserPanel_MyProfile page- Notifications panel hiding behind Verfications section | Sarvanaraj P;Jagadeesh kalyan;Prakash Raj S;Vijay Kumar N | User Panel Bugs;Verified Bugs
BUG_UserPanel_MyProfile page- invalid file format accepting in Add portfolio | Vijay Kumar N | User Panel Bugs;Verified Bugs
Task_004-Test My Work - My Jobs Fucntionalities | Vijay Kumar N | Task
Smoke Test_Build Version:1.0.4_Creator Profile, Home and Find Collaborator | Gayathri Bandhila | Smoke Test
Bug_Creator_Home_BUG_022_Active projects tab is not working | Gayathri Bandhila | User Panel Bugs;Minor;Verified Bugs
BUG_Admin_Settings page- Manage settings not working | Sarvanaraj P;Prakash Raj S;Vijay Kumar N | Admin Panel Bugs;Verified Bugs
Smoke Test_Build Version:1.0.1_Join as Collabortor, Home and MyWork | Vijay Kumar N | Smoke Test
BUG Test Collaborator Home page Functionalities - Phone verification | Vijay Kumar N | User Panel Bugs;Verified Bugs
Bug-Homepage Footer-Bug-023-Verify “Direct Contract” navigation | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
Bug_Homepage_Bug-026 MobIle Version Verify the Heading text Allignment on Homepage | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | User Panel Bugs;Verified Bugs;Major
BUG_ mobile testing_ Collaborator My Profile _ Content is shifted to left and empty space is visible on right side. | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Akash Barik | User Panel Bugs;New Bugs;Major
Bug_Financials_Withdraw_BUG_011_The system behavior when a user enters a negative UPI number. | Aravind Sunkara;Sarvanaraj P;Prakash Raj S;Deepak Rajan | User Panel Bugs;Re-Opened Bugs;Major
Bug-Homepage -Bug-014 _Click on Discover and connect | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S;Akash Barik | User Panel Bugs;Minor;Verified Bugs
Bug_Creator_Home_BUG_026_View all button is not working | Gayathri Bandhila | User Panel Bugs;Minor;Verified Bugs
Bug-Login_Bug-023 Verifiy Back button avaliability for Login | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S;Sandeep Reddy Bakkachennaiahgari | User Panel Bugs;Re-Opened Bugs;Minor
Suggestion-Admin panel_Settings appearing twice in Dashboard | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | Suggestion
Task_005-Test Sign Up with Email | Sarvanaraj P;Mahesh Reddy Paduru | Task
Bug-Login_Bug-011Verify Password Enter And check Validation message for Email | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S;Sandeep Reddy Bakkachennaiahgari | User Panel Bugs;Verified Bugs;Major
Bug-Homepage-Bug-22,Verify “How to Find Work” navigation | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
Bug _Footer Section _Bug-030Verify “For Creator” and “For Collaborator” links functionality in Footer section | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S;Sandeep Reddy Bakkachennaiahgari | User Panel Bugs;Re-Opened Bugs;Minor
Bug_Admin_Dashboard_BUG_021_Progress data is not there in active projects | Gayathri Bandhila | Admin Panel Bugs;Minor;Verified Bugs
Bug_ Admin Analytics& revenue splits_BUG_014_The chart shows percentages, but they appear inconsistent or static | ayyappa tellamekala | Admin Panel Bugs;Verified Bugs;Major
BUG_UserPanel_MyProfile page- Numbers alone should not accept in Profile Name | Sarvanaraj P;Prakash Raj S;Nala Sravan Kumar;Vijay Kumar N | User Panel Bugs;Verified Bugs
BUG_UserPanel MyWork page - Pop up notification is hidden when action made | Sarvanaraj P;Kolimi Shaik Fazil;Prakash Raj S;Vijay Kumar N | User Panel Bugs;Verified Bugs
Smoke Test Build Version: 1.0.3_Admin_Analytics & Revenue splits | ayyappa tellamekala | Smoke Test
Bug_Creator_Home_BUG_037_See more button is not working on complete profile | Gayathri Bandhila | User Panel Bugs;Minor;Verified Bugs
BUG_Creator_My project_All contract_BUG_005_Download button is not working | Sarvanaraj P;Barath Kaileash G.V;Prakash Raj S;Deepak Rajan | User Panel Bugs;Verified Bugs
Bug_ Creator My Profile _Bug_011_ System accepts 10MB image file, and the profile image uploaded without any errors | ayyappa tellamekala | User Panel Bugs;Minor;Verified Bugs
Smoke Test_Build Version: 1.0.2_Admin_User | Barath Kaileash G.V | Smoke Test
Bug_Creator_Home_BUG_012_Show all button is not working properly | Gayathri Bandhila | User Panel Bugs;Minor;Verified Bugs
Bug_Admin_Login _Bug-006 Show Button is Displaying instead of toogle icon | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | Admin Panel Bugs;Verified Bugs
Bug_Admin Subscription_BUG_008_Data should be sorted correctly in ascending/descending order | Aravind Sunkara;Sarvanaraj P;Prakash Raj S;Nala Sravan Kumar | Admin Panel Bugs;Minor;Verified Bugs
Bug_ Collaborator My Profile _Bug_014_Stystem did not display the image properly in chat section | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Minor;Verified Bugs
Bug-login-Bug-030-Verify logout functionality and proper session reset on clicking Sign In after logout | Sarvanaraj P;Mahesh Reddy Paduru;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;Re-Opened Bugs;Major
Bug_ Collaborator My Profile _Bug_034_ After entering Invalid numbers, special characters, alphabets in the all fields are saved without any error message | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Verified Bugs;Major
Bug_ Collaborator My Profile _Bug_025_ Error message not displayed system accept invalid starting to end year without showing any error | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Minor;Verified Bugs
Bug_Creator_Home_BUG_025_Cancelled spelling is not correct | Gayathri Bandhila | User Panel Bugs;Minor;Verified Bugs
Bug_Homepage__Bug-027 Mobile Version Verify Allignments of cards in homepage section | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | User Panel Bugs;Verified Bugs;Major
Admin_Profile_Verify_BUG-015 First Name & Last Name field should not accept numeric values | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | Admin Panel Bugs;Verified Bugs;Major
Smoke Test Build version : 1.0.0_Admin Login & Notifications | Mahesh Reddy Paduru | Smoke Test
Bug_Admin Subscription_BUG_007_Displayed plan count does not match the actual data. | Aravind Sunkara;Sarvanaraj P;Prakash Raj S;Nala Sravan Kumar | Admin Panel Bugs;Verified Bugs;Critical
Bug -Login-Verify Sending OTP action functionality Deliverd succesfully | Mahesh Reddy Paduru | User Panel Bugs;Minor;Verified Bugs
Bug_Admin _Login_Bug_002 Password Validation popup appear many times | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | Admin Panel Bugs;Verified Bugs;Critical
Bug_Creator_Home_BUG_049_No option to specify the duration of days, weeks, months | Sarvanaraj P;Kolimi Shaik Fazil;Gayathri Bandhila;Prakash Raj S | User Panel Bugs;Re-Opened Bugs;Minor
Smoke Test_Build Version: 1.0.3_Admin_Option | Sarvanaraj P;Barath Kaileash G.V | Smoke Test
BUG_AdminPanel_User_BUG_008_Save change | Barath Kaileash G.V | Verified Bugs
Bug_ Collaborator My Profile _Bug_042_ Social link box its accepting Invalid URL | Sarvanaraj P;Kolimi Shaik Fazil;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;Verified Bugs;Major
Bug_Admin_Dashboard_BUG_015_Month and week data is not there in the progress chart | Gayathri Bandhila | Admin Panel Bugs;Minor;Verified Bugs
Bug-Homepage -Bug-015-Verify Click on Collabrate Seamlesly | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S;Akash Barik | User Panel Bugs;Minor;Verified Bugs
Bug_ Creator My Profile _Bug_008_After saving skill did not added to the list in edit skill section | Sarvanaraj P;ayyappa tellamekala;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
BUG_Admin panel_User_BUG_017_Vision Icon | Sarvanaraj P;Barath Kaileash G.V;Prakash Raj S | Admin Panel Bugs;Re-Opened Bugs;Minor
BUG_Admin_Settings page- Time zone not changing | Sarvanaraj P;Prakash Raj S;Akash Barik;Vijay Kumar N | Admin Panel Bugs;New Bugs;Verified Bugs
Smoke Test_Build_Version:1.0.4_UserPanel_Join as Collabortor Profile, Home and MyWork | Vijay Kumar N | Smoke Test
BUG_Admin_Settings page-Unable to Download account report | Vijay Kumar N | Admin Panel Bugs;Verified Bugs
Bug_ Creator My Profile _Bug 32_ After clicking save button, the selected file did not save successfully and displayed error message | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;New Bugs;Minor
BUG_UserPanel_Collaborator_HomePage- Unread notification is not disappearing | Sarvanaraj P;Prakash Raj S;Vijay Kumar N | User Panel Bugs;Re-Opened Bugs;Major
Bug_ Creator My Profile _ Delete button is not working properly in edit portfolio page | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;New Bugs;Major
Bug_Creator_Home_BUG_019_For mobile number when we click on resend otp then also otp is not received | Sarvanaraj P;Gayathri Bandhila;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;Re-Opened Bugs;Major
Bug_ Collaborator My Profile _Bug_007_ When multiple reviews added, the View all button not functioning properly | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Re-Opened Bugs;Minor
BUG Join as Collaborator Profile Page Function - Upload profile image | Vijay Kumar N | User Panel Bugs;Verified Bugs
Smoke -Test Build Version:1.0.4_ Signup and Login | Mahesh Reddy Paduru | Smoke Test
Bug_Admin Subscription_BUG_003_The Name field accepts only alphabetic characters and rejects any Special characters | Aravind Sunkara;Sarvanaraj P;Prakash Raj S | Admin Panel Bugs;Verified Bugs;Critical
Bug_Financials_Withdraw_BUG_003_The Withdraw button is not disabled when the available balance is insufficient | Aravind Sunkara;Sarvanaraj P;Prakash Raj S;Deepak Rajan | User Panel Bugs;Verified Bugs;Major
Bug_Creator_Home_BUG_052_ Cancelled project status not reflects in Creator dashboard | Sarvanaraj P;Gayathri Bandhila;Prakash Raj S | User Panel Bugs;New Bugs;Minor
Smoke Test_Build Version:1.0.2_Creator Profile, Home and Find Collaborator | Gayathri Bandhila | Smoke Test
Smoke -Test Build Version:1.0.2_ Signup and Login | Mahesh Reddy Paduru | Smoke Test
Smoke Test Build Version:1.0.4_Collabortor Subscription and Financials | Aravind Sunkara | Smoke Test
Bug_Admin_Notifications Bug-010 Admin Profile not clickable | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | Admin Panel Bugs;Verified Bugs;Major
Bug_ Collaborator My Profile _Bug_045_ All field accepting negative but they have to accept only positive | ayyappa tellamekala | User Panel Bugs;Verified Bugs;Major
Bug_ Admin_ Analytics& revenue splits_BUG_005_Verify After refreshing, the page still going to dashboard | Sarvanaraj P;ayyappa tellamekala;Jagadeesh kalyan;Prakash Raj S | Admin Panel Bugs;Minor;Verified Bugs
Bug_Creator_Home_BUG_011_Complete your profile button is not working | Gayathri Bandhila | User Panel Bugs;Minor;Verified Bugs
BUG_USerpanel_Homepage- View All button in All jobs is not working | Vijay Kumar N
Bug_ Creator My Profile _Bug_012_ When user click on an unread or read message system should open the details of that message or allow interaction , and notification page should remain open until action completed | ayyappa tellamekala | User Panel Bugs;Minor;Verified Bugs
Bug-Homepage-Bug-002 By Clicking on Professional Functionality not redirecting to respective Page | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | User Panel Bugs;Re-Opened Bugs;Verified Bugs
Bug_ Admin _Analytics& revenue splits_BUG_013_Tooltip is missing or does not display values; only side panel shows percentages. | Sarvanaraj P;ayyappa tellamekala;Jagadeesh kalyan;Prakash Raj S | Admin Panel Bugs;Minor;Verified Bugs
Bug_Financials_Overview_BUG_001_Bank Account Number allows more than 16 digits. | Aravind Sunkara | User Panel Bugs;Verified Bugs;Major
Bug_ Creator My Profile _Bug 23_ System accepting invalid input in skill section | Sarvanaraj P;ayyappa tellamekala;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
BUG_Admin panel_User_BUG_011_In active status | Barath Kaileash G.V | Verified Bugs
Bug_Admin Subscription_BUG_002_The Price field accepts only numeric valves and rejects Special characters. | Aravind Sunkara;Sarvanaraj P;Prakash Raj S;Nala Sravan Kumar | Admin Panel Bugs;Verified Bugs;Critical
Bug_ Creator My Profile _Notification_ Bug_006_ the message does not navigate to a detailed view | ayyappa tellamekala | User Panel Bugs;Minor;Verified Bugs
Bug_Creator_Home_BUG_040_Negative values are accepting for price in filter | Sarvanaraj P;Gayathri Bandhila;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
Bug_Admin_Dashboard_BUG_012_Week option data is not there in project status | Gayathri Bandhila | Admin Panel Bugs;Minor;Verified Bugs
Bug-signup-While entering Email in caps letters otp deliverd succesfully ,While entering OTP | Mahesh Reddy Paduru | User Panel Bugs;Minor;Verified Bugs
BUG_Admin panel_User_BUG_012_Banned status | Barath Kaileash G.V | Verified Bugs
BUG_UserPanel_MyProfile page- Edited changes still persists even cancels the edited change | Sarvanaraj P;Prakash Raj S;Vijay Kumar N | User Panel Bugs;Re-Opened Bugs;Minor
BUG_Creator_Financials_BUG_007_Popup message is not appired when payment is done | Sarvanaraj P;Barath Kaileash G.V;Prakash Raj S | User Panel Bugs;New Bugs;Minor
Smoke Test_Build Version:1.0.0_SignUp and Login | Mahesh Reddy Paduru | Smoke Test
Bug_ Collaborator My Profile _Bug_004_OTP did not received to given number | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Re-Opened Bugs;Major
BUG_UserPanel_MyProfile - Budget in Collaborators weekly/hr mismatching on creator's best match list. | Sarvanaraj P;Prakash Raj S;Vijay Kumar N | User Panel Bugs;New Bugs;Major
Bug_ Collaborator My Profile _Bug_006_ When multiple portfolio items added, the View all button not functioning properly | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Minor;Verified Bugs
Bug_ Collaborator My Profile _Bug_018_ After clicking save button the Portfolio link URL missing in profile page | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Minor;Verified Bugs
Smoke Test_ Build Version:1.0.2_Creator Subscription and Creator and Collaborator My Profile, Message & Notification | ayyappa tellamekala | Smoke Test
Bug_Admin_Dashboard_BUG_019_Price data is not there in the active projects | Gayathri Bandhila | Admin Panel Bugs;Minor;Verified Bugs
BUG_UserPanel_Collaborator_Home - Local time and Job description is not displaying | Sarvanaraj P;Prakash Raj S;Nala Sravan Kumar;Vijay Kumar N | User Panel Bugs;Verified Bugs
Task_002-Test My project -Proposal functionalities | Barath Kaileash G.V | Task
Bug_ Admin _Analytics& revenue splits_BUG_006_The total revenue is not updated and showing zero | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S | Admin Panel Bugs;Verified Bugs;Major
Bug_Creator_Home_BUG_039_Post job now button is not working | Sarvanaraj P;Gayathri Bandhila;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;Verified Bugs;Major
Task_001-Test Collaborator Subscription Page Functionalities | Aravind Sunkara | Task
Bug-Beforesignup-While clicking continue with apple Button it should redirected to apple signin page | Mahesh Reddy Paduru | User Panel Bugs;Minor;Verified Bugs
Bug_ Collaborator My Profile _Bug_010_ When multiple work experience added, the View all button not functioning properly | ayyappa tellamekala | User Panel Bugs;Minor;Verified Bugs
Smoke Test Build Version: 1.0.4_Admin_Analytics & Revenue splits | ayyappa tellamekala | Smoke Test
Smoke Test_Build Version:1.0.0_Collabortor Subscription and Financials | Aravind Sunkara | Smoke Test
BUG_UserPanel_Home_page- Social media connect is not working | Sarvanaraj P;Prakash Raj S;Vijay Kumar N | User Panel Bugs
Task_001-Test Creator Subscription Functionalities | ayyappa tellamekala | Task
BUG_Userpanel_Homepage - Unable to view and download the creator uploaded file from collaborators page | Sarvanaraj P;Prakash Raj S;Vijay Kumar N | User Panel Bugs;New Bugs;Critical
Smoke Test_Build Version:1.0.2_Collabortor Subscription and Financials | Aravind Sunkara | Smoke Test
Bug_ Admin _Analytics& revenue splits_BUG_001_ Default image displayed for all collaborators in top collaborator section | ayyappa tellamekala | Verified Bugs
Bug_ Admin _Analytics& revenue splits_BUG_010_ All values showing as zero, and the chart area remains blank. | Sarvanaraj P;ayyappa tellamekala;Jagadeesh kalyan;Prakash Raj S | Admin Panel Bugs;Major;Verified Bugs
Bug_ Creator My Profile _Bug_002_Phone verification is working , but OTP did not sent to given number | Sarvanaraj P;ayyappa tellamekala;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;Re-Opened Bugs;Major
Bug_ Collaborator My Profile _Bug_027_ Error message not displayed system accept invalid starting to end year without showing any error | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Minor;Verified Bugs
Task_001-Test Join as Collaborator Profile Page Functionalities | Vijay Kumar N | Task
BUG_UserPanel_HomePage - UI design option is repeated twice in filter section | Sarvanaraj P;Jagadeesh kalyan;Prakash Raj S;Vijay Kumar N | User Panel Bugs;Re-Opened Bugs;Major
Suggestion_User panel (Creator)_The email should have the static email ID in the verify email ID field | Sarvanaraj P;Barath Kaileash G.V;Prakash Raj S | Suggestion
Bug_Subscription-Collaborator Page_BUG_001_ Back button functionality not working | Aravind Sunkara;Sarvanaraj P;Kolimi Shaik Fazil;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
BUG_creator_Financials_Add funds__BUG_009_Card expiry not working | Sarvanaraj P;Barath Kaileash G.V;Prakash Raj S;Deepak Rajan | User Panel Bugs;Verified Bugs
Bug_Creator_Home_BUG_016_More option in view all jobs is not working | Sarvanaraj P;Gayathri Bandhila;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
Suggestion_Admin panel_ Forgot password must be there for an login | Sarvanaraj P;Barath Kaileash G.V;Prakash Raj S | Suggestion
Smoke _Test Build Version-1.0.2-Admin Login & Notification | Mahesh Reddy Paduru | Smoke Test
Bug-Homepage -Bug-016 Verify Click on Tack and Grow | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S;Akash Barik | User Panel Bugs;Minor;Verified Bugs
Bug_ Collaborator My Profile _Bug_038_ When enter invalid OTP not displayed Pop-up or error message | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Minor;Verified Bugs
Smoke Test_Build Version:1.0.3_Creator Profile, Home and Find Collaborator | Gayathri Bandhila | Smoke Test
Bug_Financials_Withdraw_BUG_009_The Account Number field accepts only Numeric Valves and rejects Special characters | Aravind Sunkara;Sarvanaraj P;Prakash Raj S;Deepak Rajan | User Panel Bugs;Re-Opened Bugs;Critical
Admin _Profile_BUG-012 Verify Live Weather Dispaly Functionality | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | Admin Panel Bugs;New Bugs;Major
Task_002-Test Sign Up with Google Account | Mahesh Reddy Paduru | Task
Bug_ Creator My Profile _ Creator name_Bug_001_In creator, 'Name' field numbers and special characters are accepting | Sarvanaraj P;Gayathri Bandhila;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
BUG_UserPanel_Collaborators_MyWorks - profile picture is mismatching in Collaborators Current contracts page | Sarvanaraj P;Prakash Raj S;Vijay Kumar N | User Panel Bugs;Verified Bugs
Smoke Test Build Version: 1.0.0_Admin_Subscription | Aravind Sunkara | Smoke Test
Bug-Admin-Bug-019-Verify Template button functionality |  | Admin Panel Bugs
Bug_ Collaborator My Profile _Bug_032_ phone verified successfully Pop-up message not displayed properly | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Re-Opened Bugs;Minor
Bug_ Collaborator My Profile _Bug_011_ When multiple work education details added, the View all button not functioning properly | ayyappa tellamekala | User Panel Bugs;Minor;Verified Bugs
Bug_Creator-Subscription_BUG_005_The Back button is not working properly in pro plan | Sarvanaraj P;Kolimi Shaik Fazil;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
Smoke Test Build version : 1.0.3_Admin Login & Notifications | Mahesh Reddy Paduru | Smoke Test
BUG_Admin panel_User_BUG_005_Role | Barath Kaileash G.V | Verified Bugs
Bug_ Collaborator My Profile _Bug_030_ After saving , location data not displayed | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Minor;Verified Bugs
Bug_ Collaborator My Profile _Bug_041_ After saving validation message is not displayed when all fields empty | Sarvanaraj P;Kolimi Shaik Fazil;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;Verified Bugs;Major
Bug_ Collaborator My Profile _Bug 58_ Verify that after clicking a notification , it does not allow unintended navigation or misdirected access to other sections | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;New Bugs;Major
Smoke Test_ Build Version:1.0.0_Creator Subscription and Creator and Collaborator My Profile, Message & Notification | ayyappa tellamekala | User Panel Bugs;Smoke Test
Bug-signup__Bug-009 while entering the invalid Mail genrating the verification code | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S;Sandeep Reddy Bakkachennaiahgari | User Panel Bugs;Verified Bugs;Major
Bug_ Collaborator My Profile _Bug_001_ After saving experience data is not displayed | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Minor;Verified Bugs
Bug_Creator_Home_BUG_006_Edit options are not working properly in view jobs | Gayathri Bandhila | User Panel Bugs;Minor;Verified Bugs
BUG_Admin Panel_User_BUG_016_If the user is not adding the profile picture then it should show default picture | Sarvanaraj P;Barath Kaileash G.V;Prakash Raj S | Admin Panel Bugs;New Bugs
Bug_Creator_Home_BUG_029_Last name field accepts numbers and special characters | Gayathri Bandhila | User Panel Bugs;Minor;Verified Bugs
Bug_Homepage Mobile Version Verify full visibility of text in “Key Features” section | Mahesh Reddy Paduru
Bug_Creator_Home_BUG_032_Save button is working Without entering any details | Gayathri Bandhila | User Panel Bugs;Minor;Verified Bugs
Bug_Admin_Dashboard_BUG_001_User is not updating automatically | Sarvanaraj P;Gayathri Bandhila;Prakash Raj S;Deepak Rajan | Admin Panel Bugs;Verified Bugs;Major
Bug-SignupButton_Bug-024Verify by clicking on Signup button not Redirecting to the signup Page | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S;Sandeep Reddy Bakkachennaiahgari | User Panel Bugs;Verified Bugs;Major
BUG_Admin_Settings page- Exporting account data not working | Sarvanaraj P;Prakash Raj S;Vijay Kumar N | Admin Panel Bugs;New Bugs;Verified Bugs;Major
Bug_ Collaborator My Profile _Bug 59_ System accepts pdf file and profile image not displayed properly | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;New Bugs;Minor
Smoke Test_Build Version:1.0.4_Admin_Panel_Settings_module | Vijay Kumar N | Smoke Test
Bug_Creator_Home_BUG_047_Set up your profile button is not enabling after filling all mandatory fields also | Sarvanaraj P;Kolimi Shaik Fazil;Gayathri Bandhila;Prakash Raj S | User Panel Bugs;Re-Opened Bugs;Minor
Admin-Profile_Bug-016_Verify Logout option should not be displayed twice in Admin Panel | Sarvanaraj P;Kolimi Shaik Fazil;Mahesh Reddy Paduru;Prakash Raj S | Admin Panel Bugs;Verified Bugs;Major
BUG_Admin panel_User_BUG_016_Email ID field | Barath Kaileash G.V | Verified Bugs
Bug-Footer-Bug-031_Verify Email field displays correct email format in Footer section | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S;Sandeep Reddy Bakkachennaiahgari | User Panel Bugs;Re-Opened Bugs;Minor
BUG_Admin panel_User_BUG_006_Status
Bug_ Collaborator My Profile _Bug_022_ After saving, rating not updating in profile | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Minor;Verified Bugs
Bug_ Collaborator My Profile _Bug_023_ Profile percentage remain same | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Minor;Verified Bugs
BUG Test Collaborator Home page Functionalities - Email verification | Vijay Kumar N | User Panel Bugs;Verified Bugs
Bug-Homapage_Bug-019Verify User count Not having constant after adding the users and Refreshing the Page | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S;Nala Sravan Kumar | User Panel Bugs;Minor;Verified Bugs
Admin Dashboard-Bug-Bug-017 Verify “Remove Picture” action when no profile picture is present | Sarvanaraj P;Kolimi Shaik Fazil;Mahesh Reddy Paduru;Prakash Raj S | Admin Panel Bugs;Verified Bugs;Major
Bug_Creator-Subscription_BUG_004_After clicking Subscribe to Agent button payment details are saved but confirmation message not displayed and displayed | Sarvanaraj P;Kolimi Shaik Fazil;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
Task_003-Test My Work- All Contracts Fucntionalities
Bug_Creator_Home_BUG_023_Completed tab is not working | Gayathri Bandhila | User Panel Bugs;Minor;Verified Bugs
BUG_UserPanel_Home_page- Unable to select See more button in best matches category | Prakash Raj S;Deepak Rajan;Vijay Kumar N | User Panel Bugs;Verified Bugs
Smoke Test_Build Version:1.0.0_Join as a creator, my project & Financials | Barath Kaileash G.V | Smoke Test
BUG_Admin_Settings page - Unable to Save changes | Vijay Kumar N | Admin Panel Bugs;Verified Bugs
Bug_Creator_Home_BUG_010_Find collaborator in home module is not working as expected as expected | Sarvanaraj P;Gayathri Bandhila;Prakash Raj S;Nala Sravan Kumar | User Panel Bugs;Minor;Verified Bugs
BUG_Admin panel_User_BUG_013_Email ID | Barath Kaileash G.V | Verified Bugs
Bug_Admin _Login _Bug_001 Email required validation repeated multiple times | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | Admin Panel Bugs;Verified Bugs;Critical
Bug_ Admin_ Analytics& revenue splits_BUG_008_ When clicking on the collaborator box, no action or response occur, even through value is visible | Sarvanaraj P;ayyappa tellamekala;Jagadeesh kalyan;Prakash Raj S | Admin Panel Bugs;Verified Bugs;Major
Bug_ Collaborator My Profile _Bug 56_ | ayyappa tellamekala
Bug_Admin_Dashboard_BUG_003_Complete projects are not showing | Sarvanaraj P;Gayathri Bandhila;Prakash Raj S;Deepak Rajan | Admin Panel Bugs;Re-Opened Bugs;Minor
BUG_UserPanel_Homepage - Fixed rate confirmation should ask the collaborator if their expectations are higher | Sarvanaraj P;Prakash Raj S;Vijay Kumar N | User Panel Bugs;New Bugs;Major
Bug_Creator_Home_BUG_028_First name field accepts numbers and special characters for complete profile | Gayathri Bandhila | User Panel Bugs;Minor;Verified Bugs
Bug_Creator_Home_BUG_036_Portfolio is not able to save | Gayathri Bandhila | User Panel Bugs;Minor;Verified Bugs
Smoke Test_Build Version:1.0.0_Join as Collabortor, Home and MyWork | Vijay Kumar N | User Panel Bugs;Smoke Test
Bug_ Collaborator My Profile _Bug_026_ The end date remains editable and user can change it | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Minor;Verified Bugs
Bug_Creator_Login not working
Bug_Admin _Notifications_Bug-007 Notification are Not clickable | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | Admin Panel Bugs;Minor;Verified Bugs
Bug_ Collaborator My Profile _Bug_019_ The data displayed in badge box, but after clicking save button badge is missing in profile page | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Minor;Verified Bugs
Smoke Test_ Build Version:1.0.3_Creator Subscription and Creator and Collaborator My Profile, Message & Notification | ayyappa tellamekala | Smoke Test
Bug_ Creator My Profile _Bug 28_ Verify that the country selected during intial profile setup is displayed on the profile page | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;New Bugs;Minor
Bug_ Collaborator My Profile _Bug_031_ The end date remains editable and user can change it | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Minor;Verified Bugs
Bug-Homepage_ Bug-018Verify User Count Not having constat after adding the users and Refreshing the page | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S;Nala Sravan Kumar | User Panel Bugs;Minor;Verified Bugs
Bug_Creator_ Find Collaborator_Filters _BUG_003_Selected filters cannot be deselected. | Sarvanaraj P;Gayathri Bandhila;Prakash Raj S;Nala Sravan Kumar | User Panel Bugs;Minor;Verified Bugs
Smoke Test Build Version :1.0.4_Admin Dashboard | Gayathri Bandhila | Smoke Test
Suggestion_Admin panel_Keep a drop down box and select the required field | Sarvanaraj P;Barath Kaileash G.V;Prakash Raj S | Suggestion
Bug_ Admin_ Analytics& revenue splits_BUG_003_The revenue box is visible, but no clicking action occurs | Sarvanaraj P;ayyappa tellamekala;Jagadeesh kalyan;Prakash Raj S | Admin Panel Bugs;Verified Bugs;Major
Bug-Admin Panel-Bug-019 Verify Template button functionality | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | Admin Panel Bugs;Verified Bugs;Major
Smoke Test Build Version :1.0.0_Admin Dashboard | Gayathri Bandhila | Admin Panel Bugs;Smoke Test
BUG_UserPanel_Homepage - Jobs are showing '0' even there are active jobs in the list | Sarvanaraj P;Prakash Raj S;Vijay Kumar N | User Panel Bugs;New Bugs;Minor
Suggestion_User Panel_Home_Post job now_We can remove "To" option when we choose fixed price | Sarvanaraj P;Gayathri Bandhila;Prakash Raj S | Suggestion;User Panel Bugs
Bug_Financials_Withdraw_BUG_005_The system behavior when a user enters a negative amount value. | Aravind Sunkara;Sarvanaraj P;Prakash Raj S;Deepak Rajan | User Panel Bugs;Verified Bugs;Major
Bug_ Creator My Profile _Bug 27_ The pop-ups did not displayed on email verification page and instead appeared in profile page | Sarvanaraj P;Kolimi Shaik Fazil;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
Bug_Admin_Dashboard_BUG_017_Client details is not there in the active projects | Gayathri Bandhila | Admin Panel Bugs;Minor;Verified Bugs
Smoke Test Build Version: 1.0.3_Admin_Subscription | Aravind Sunkara | Smoke Test
Bug_ Creator My Profile _Bug_007_ After saving ,Uploaded Profile picture not displayed properly in my profile page | Sarvanaraj P;ayyappa tellamekala;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
Bug_Creator_Home_BUG_018_For mobile number verification otp is not received | Sarvanaraj P;Gayathri Bandhila;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;Re-Opened Bugs;Major
BUG_Creator_My project_All contract_Active contracts_BUG_002_Active option is not working | Sarvanaraj P;Barath Kaileash G.V;Prakash Raj S;Deepak Rajan | User Panel Bugs;Verified Bugs
Bug-Homepage Footer -Bug-20-Verify “How to Post a Project” navigation | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
Task_008-Test Verify Footer Links Not working | Mahesh Reddy Paduru
Smoke Test_Build Version:1.0.0_Creator Profile, Home and Find Collaborator | Gayathri Bandhila | User Panel Bugs;Smoke Test
Smoke Test_Build Version:1.0.0_SignUp and Login
BUG_UserPanel_MyWorks page - Submitting and applying the same job | Sarvanaraj P;Prakash Raj S;Deepak Rajan;Vijay Kumar N | User Panel Bugs;Verified Bugs
Bug_Creator_Home_BUG_009_Save as draft is not working | Sarvanaraj P;Gayathri Bandhila;Prakash Raj S;Nala Sravan Kumar | User Panel Bugs;Minor;Verified Bugs
BUG Test Collaborator Home page Functionalities - Complete your profile feature | Vijay Kumar N | User Panel Bugs;Verified Bugs;Major
Bug-Homepage _Bug-017Verify User count not having constant after Increasing the value and refresh the Page | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S;Nala Sravan Kumar | User Panel Bugs;Minor;Verified Bugs
Bug_Admin_Dashboard_BUG_016_Progress chart is not displayed correct data | Gayathri Bandhila | Admin Panel Bugs;Minor;Verified Bugs
Bug_Creator_Find collaborator_Collaborate request button_BUG_004_Collaborate request page is not working | Sarvanaraj P;Gayathri Bandhila;Prakash Raj S;Nala Sravan Kumar | User Panel Bugs;Minor;Verified Bugs
BUG_UserPanel_Homepage- Pop up message should display after searched job | Sarvanaraj P;Prakash Raj S;Nala Sravan Kumar;Vijay Kumar N | User Panel Bugs;Re-Opened Bugs;Low
Bug_ Collaborator My Profile _Bug 46_ System has to accept punctions and numbers in description field and should not display validation | Sarvanaraj P;ayyappa tellamekala;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;New Bugs;Minor
Bug_ Collaborator My Profile _ After clicking unread notification, it is not moved to read automatically | Sarvanaraj P;Kolimi Shaik Fazil;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;Verified Bugs;Major
Task_002-Test Creator Profile, Message and Notification Section | ayyappa tellamekala | Task
Bug_Creator-Subscription_BUG_015_ The “Tasks This Year” section is displaying value with “$” currency symbol (Example: $12.00) instead of displaying task count. | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S | Admin Panel Bugs;New Bugs;Minor
Buglogin- Bug-022 Spell Check of 'Forget' should be 'Forgot' | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | User Panel Bugs;Re-Opened Bugs;Verified Bugs
Bug-Login -Verify login failure with invalid email adress | Mahesh Reddy Paduru | User Panel Bugs;Minor;Verified Bugs
Bug_Admin_Dashboard_BUG_006_Monthly revenue data is not found | Sarvanaraj P;Gayathri Bandhila;Prakash Raj S;Deepak Rajan | Admin Panel Bugs;Minor;Verified Bugs
Bug-Footer-Verify redirection of Play Store and App Store buttons in “Download Our App” section | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | User Panel Bugs;Re-Opened Bugs;Major
Bug-Login-Bug-010Verify Email Enter And check Validation message for Password | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S;Sandeep Reddy Bakkachennaiahgari | User Panel Bugs;Verified Bugs;Major
Bug_Admin_Dashboard_BUG_010_Today option data is not there in project status | Gayathri Bandhila | Admin Panel Bugs;Minor;Verified Bugs
Smoke Test_Build_Version:1.0.3_UserPanel_Join as Collabortor, Home and MyWork | Vijay Kumar N | Smoke Test
BUG_Admin panel_Oprion_BUG_001_Creator Category,Primary Niche,Secondary Niche,Platform,Followers Range,Skill Category,Portfolio Category_the order from option dialog box show the negative value | Sarvanaraj P;Barath Kaileash G.V;Kolimi Shaik Fazil;Prakash Raj S | Admin Panel Bugs;Re-Opened Bugs;Minor;Verified Bugs
Bug_ Admin Analytics& revenue splits_BUG_012_ Chart shows values but they appear inconsistent or static compared to user activity. | ayyappa tellamekala | Admin Panel Bugs;Verified Bugs;Major
Bug_ Collaborator My Profile _Bug_044_ The timing field accepting outside time range(e.g., 34:00) and did not display any error message and also not accepting numbers | Sarvanaraj P;Kolimi Shaik Fazil;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;Verified Bugs;Major
BUG_Admin Panel_User_BUG_009_Pop Up | Barath Kaileash G.V | Admin Panel Bugs;Verified Bugs
Smoke Test_Build Version:1.0.1_Admin_Panel_Settings_module | Vijay Kumar N | Smoke Test
BUG_UserPanel_MyProfile page- Add review option is removed | Sarvanaraj P;Jagadeesh kalyan;Prakash Raj S;Vijay Kumar N | User Panel Bugs;Re-Opened Bugs;Minor
BUG_Admin_Settings page- Mandatory fields not added | Sarvanaraj P;Prakash Raj S;Akash Barik;Vijay Kumar N | Re-Opened Bugs;Verified Bugs;Admin Panel Bugs
Bug_ Collaborator My Profile _Bug 49_ System accepting invalid input in skill section | Sarvanaraj P;ayyappa tellamekala;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
Bug Subscription-Collaborator Page_BUG_004_ The CVC field is masked properly or not | Aravind Sunkara;Sarvanaraj P;Prakash Raj S | User Panel Bugs;New Bugs;Critical
Bug_ Admin_ Analytics& revenue splits_BUG_007_ When clicking on the creator box, no action or response occur, even through value is visible | Sarvanaraj P;ayyappa tellamekala;Jagadeesh kalyan;Prakash Raj S | Admin Panel Bugs;Verified Bugs;Major
Bug_ Creator My Profile _Bug_015_ System accepting empty file without validation | Sarvanaraj P;ayyappa tellamekala;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;Re-Opened Bugs;Minor
BUG Admin dashboard Settings page functionalities - Change password | Vijay Kumar N | Admin Panel Bugs;Verified Bugs
Bug_Creator_Home_BUG_001_job field accepts numbers and special characters | Gayathri Bandhila | User Panel Bugs;Verified Bugs
BUG Test Collaborator Home page Functionalities - message button error | Vijay Kumar N | User Panel Bugs;Verified Bugs;Major
BUG_Admin_Settings page-Unable to change Date format | Sarvanaraj P;Prakash Raj S;Akash Barik;Vijay Kumar N | Admin Panel Bugs;Verified Bugs
Bug-signup-Bug-032-Verify that the system should not proceed to verification when an invalid email is entered. | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | User Panel Bugs;Verified Bugs;Major
Bug-Admin- Bug-018_Verify location access behavior on clicking Refresh button | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | Admin Panel Bugs;New Bugs;Major
BUG_UserPanel_Home page-Button fault in Footer section | Sarvanaraj P;Prakash Raj S;Vijay Kumar N | User Panel Bugs;Verified Bugs
Bug-signup- BUG -026 Validation message not triggering,while entering invalid email address | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | User Panel Bugs;Verified Bugs;Major
Bug_Creator_Home_BUG_045_Resend otp timer functionality is not working | Sarvanaraj P;Gayathri Bandhila;Prakash Raj S | User Panel Bugs;Re-Opened Bugs;Minor
Bug_Creator-Subscription_BUG_003_Cardholder name field accepts invalid input(like numbers and special characters) | Sarvanaraj P;Kolimi Shaik Fazil;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;Re-Opened Bugs;Minor
Bug_ Creator My Profile _Bug 21_After clicking "Resend OTP" button no action happen and it displayed error message | Sarvanaraj P;ayyappa tellamekala;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;New Bugs;Minor
Bug-Login-Bug-017While Login Keep both field empty it should the validation pop up | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | User Panel Bugs;Verified Bugs;Major
BUG_Admin Panel_User_BUG_014_Email ID | Barath Kaileash G.V | Verified Bugs
Bug_ Collaborator My Profile _Bug_005_ See more button is not working properly | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Re-Opened Bugs;Minor
Bug_Creator_Home_BUG_015_Invite button is not working | Gayathri Bandhila | User Panel Bugs;Minor;Verified Bugs
Smoke Test_Build Version:1.0.3_Join as a creator, my project & Financials | Barath Kaileash G.V | Smoke Test
Bug_ Collaborator My Profile _Bug 54_ Verify skill rating field accepts only values between o to 5 | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;New Bugs;Minor
Bug_Admin_Dashboard_BUG_014_All time data is not there in the project status | Gayathri Bandhila | Admin Panel Bugs;Minor;Verified Bugs
Bug_Creator_Home_BUG_007_More option in posted job is not working | Sarvanaraj P;Gayathri Bandhila;Prakash Raj S;Nala Sravan Kumar | User Panel Bugs;Minor;Verified Bugs
Bug_Creator_Home_BUG_050_ Best Match profile not displaying correct hourly rate | Sarvanaraj P;Gayathri Bandhila;Prakash Raj S | User Panel Bugs;New Bugs;Minor
Bug_ Creator My Profile _Bug 25_ System has display as phone or phone verification, email has display as email or verification | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;New Bugs;Minor
Bug_Creator_Home_BUG_042_Numbers and special characters are accepting in skills field in filter | Sarvanaraj P;Gayathri Bandhila;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
Bug_Financials_Withdraw_BUG_006_The Name field accepts only alphabetic characters and rejects any numeric input. | Aravind Sunkara;Sarvanaraj P;Prakash Raj S;Deepak Rajan | User Panel Bugs;Re-Opened Bugs;Major
Smoke -Test Build Version:1.0.3_ Signup and Login | Mahesh Reddy Paduru | Smoke Test
Bug_Admin_Dashboard_BUG_005_Yearly revenue data is not found | Sarvanaraj P;Gayathri Bandhila;Prakash Raj S;Deepak Rajan | Admin Panel Bugs;Minor;Verified Bugs
Bug-Before Signup Bug-027-Verify Forgot Password on Signup Page | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S;Sandeep Reddy Bakkachennaiahgari | User Panel Bugs;Minor;Verified Bugs
Task_003-Test Financials - Transaction Functionalities | Aravind Sunkara | Task
Bug_Financials_Withdraw_BUG_010_The IFSC Code field accepts alphabetic and Numeric Valves and rejects Special characters | Aravind Sunkara;Sarvanaraj P;Prakash Raj S;Deepak Rajan | User Panel Bugs;Re-Opened Bugs;Critical
Bug-Beforesignup-Verify Clicking on Facebook account | Mahesh Reddy Paduru | User Panel Bugs;Minor;Verified Bugs
Bug_Creator_Home_BUG_044_Name field in best match is not displaying correctly | Sarvanaraj P;Kolimi Shaik Fazil;Gayathri Bandhila;Prakash Raj S | User Panel Bugs;New Bugs;Minor
BUG_UserPanel_My_Profile page- Unable to save the changes in Edit profile | Sarvanaraj P;Jagadeesh kalyan;Prakash Raj S;Vijay Kumar N | User Panel Bugs;New Bugs;Major
Bug_ Creator My Profile _Bug 24_ Unread message count badge has to display on message icon when receiving new messages | Sarvanaraj P;Kolimi Shaik Fazil;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
Task_003-Test Sign Up with Facebook Account | Mahesh Reddy Paduru | Task
Bug_Creator_Home_BUG_043_Negative values are accepting in price in job post details | Sarvanaraj P;Kolimi Shaik Fazil;Gayathri Bandhila;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
BUG_ mobile testing_ Collaborator My Profile _ When click on Hamburger menu icon, it is overlapped by profile content | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Akash Barik | User Panel Bugs;New Bugs;Major
BUG_Admin_Settings page- Unable to change Default dashboard | Sarvanaraj P;Prakash Raj S;Akash Barik;Vijay Kumar N | Admin Panel Bugs;Verified Bugs
Smoke Test Build Version: 1.0.1_Admin_Analytics & Revenue splits | ayyappa tellamekala | Smoke Test
Bug_ Creator My Profile _Bug_003_ See more button is not working properly | Sarvanaraj P;ayyappa tellamekala;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;Re-Opened Bugs;Minor
Task_007-Test Financials -Withdraw funds functionalities | Barath Kaileash G.V | Task
Bug_Creator_Home_BUG_002_Describe about the project field accepts numbers and special characters | Gayathri Bandhila | User Panel Bugs;Verified Bugs
BUG_mobile_testing_My_Profile page- Header options is not fixed at the top of the page | Sarvanaraj P;Prakash Raj S;Akash Barik;Nala Sravan Kumar;Vijay Kumar N | User Panel Bugs;Verified Bugs
Smoke Test_Build Version:1.0.1_Collabortor Subscription and Financials | Aravind Sunkara | Smoke Test
Task_002-Test Creator Home Page functionalities | Gayathri Bandhila | Task
Bug_ Collaborator My Profile _Bug 56_ The portfolio item has to save successfully and display in list , after refresh it should appear in the list | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;New Bugs;Major
Bug_Creator_Home_Filter_BUG_051_Filter option is not working after “No Matches Found” message | Sarvanaraj P;Gayathri Bandhila;Prakash Raj S | User Panel Bugs;New Bugs;Minor
Task_004-Test Sign Up with Apple Account | Mahesh Reddy Paduru | Task
Bug_ Creator My Profile _Bug 29_ Verify OTP page displays the correct delivery method (Phone or Email) | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;New Bugs;Minor
Bug-Before Signup-Bug-007-Verify visibility of footer links on Before Signup page at 100% zoom | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S
Bug_Creator_Home_BUG_053_Multiple collaborators cannot submit proposals for the same job | Sarvanaraj P;Gayathri Bandhila;Prakash Raj S | User Panel Bugs;New Bugs;Minor
Smoke Test Build Version :1.0.2_Admin Dashboard | Gayathri Bandhila | Smoke Test
Smoke Test_Build Version:1.0.4_Join as a creator, my project & Financials | Barath Kaileash G.V | Smoke Test
Bug_Creator_Home_BUG_005_When we click edit the previous details are not there | Gayathri Bandhila | User Panel Bugs;Minor;Verified Bugs
BUG_Admin panel_User_BUG_006_Status drop down
Bug-Beforesignup- Bug-006_Continue With Cookie Use Not redirecting to Respective page | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | User Panel Bugs;Re-Opened Bugs;Minor
Suggestion_UserPanel_Collaborator_Home - Price $ range from - to should not mention if it is a fixed price | Sarvanaraj P;Prakash Raj S;Vijay Kumar N | Suggestion;User Panel Bugs
Bug_ Collaborator My Profile _Bug_043_ portfolio link box its accepting Invalid URL | Sarvanaraj P;Kolimi Shaik Fazil;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;Verified Bugs;Major
Bug_Subscription-Collaborator Page_BUG_002_ The pricing unit for the Basic Plan | Aravind Sunkara;Sarvanaraj P;Kolimi Shaik Fazil;Prakash Raj S | User Panel Bugs;Verified Bugs;Critical
Bug_ Creator My Profile _Bug_014_ After clicking save , System accepted numeric values/ special characters without displaying any validation error | ayyappa tellamekala | User Panel Bugs;Minor;Verified Bugs
Suggestion_User panel (Creator)_If the project get exceed more days then the salary should get deduced | Sarvanaraj P;Barath Kaileash G.V;Prakash Raj S | Suggestion
Bug Footer-Bug-032Verify social media and app store buttons functionality in Footer section | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S;Sandeep Reddy Bakkachennaiahgari | User Panel Bugs;Re-Opened Bugs;Minor
Bug_ Admin Analytics& revenue splits_BUG_011_ All tasks count showing zero and including increment | ayyappa tellamekala | Admin Panel Bugs;Minor;Verified Bugs
BUG_UserPanel_MyWork- Submit button is not working in All Contracts | Prakash Raj S;Deepak Rajan;Vijay Kumar N | User Panel Bugs;Verified Bugs
Bug_Homepage Verify that the font size remains consistent across the pricing section | Mahesh Reddy Paduru | User Panel Bugs;Minor;Verified Bugs
Bug-Login-Bug-028 -Verify error message clears after entering correct password | Sarvanaraj P;Kolimi Shaik Fazil;Mahesh Reddy Paduru;Prakash Raj S | User Panel Bugs;Verified Bugs;Major
Bug_Creator_Home_BUG_048_In filter option in ratings some options are not working | Sarvanaraj P;Kolimi Shaik Fazil;Gayathri Bandhila;Prakash Raj S | User Panel Bugs;Re-Opened Bugs;Minor
BUG Test Collaborator Home page Functionalities - Thumbs up button | Vijay Kumar N | User Panel Bugs;Minor;Verified Bugs
Bug_Admin_Login_Bug-003 Validation not triggered for Both Fields | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | Admin Panel Bugs;Re-Opened Bugs;Verified Bugs
Bug-Homepage -Bug-003 Clicking on Registered User Functionality not redirecting to Respective Page | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | User Panel Bugs;Re-Opened Bugs;Verified Bugs
Smoke _Test Build Version-1.0.4-Admin Login & Notification | Mahesh Reddy Paduru | Smoke Test
Task_006-Test Financials -Transaction History functionalities | Barath Kaileash G.V | Task
Bug_Subscription-Collaborator Page_BUG_003_ The pricing unit for the Pro Plan | Aravind Sunkara;Sarvanaraj P;Kolimi Shaik Fazil;Prakash Raj S | User Panel Bugs;Verified Bugs;Critical
Smoke Test Build Version: 1.0.0_Admin_Analytics & Revenue splits | ayyappa tellamekala | Admin Panel Bugs;Smoke Test
Bug_ Collaborator My Profile _Bug_003_ Invalid value accepted and displayed in profile page | ayyappa tellamekala | User Panel Bugs;Minor;Verified Bugs
Smoke Test_Build_Version:1.0.2_UserPanel_Join as Collabortor, Home and MyWork | Vijay Kumar N | Smoke Test
Bug_Creator_Home_BUG_034_Random text accepts in work link field | Gayathri Bandhila | User Panel Bugs;Minor;Verified Bugs
Bug_ Collaborator My Profile _Bug 57_ | ayyappa tellamekala
BUG_UserPanel_MyWorks page - UI Design fault in Current contracts | Sarvanaraj P;Kolimi Shaik Fazil;Prakash Raj S;Vijay Kumar N | User Panel Bugs;Verified Bugs
Task_007-Test After Login CCW HomePage functionalities | Mahesh Reddy Paduru | Task
Bug_ Admin _Analytics& revenue splits_BUG_002_ After navigating to the previous/next month, any date clicked is still highlighted | Sarvanaraj P;ayyappa tellamekala;Jagadeesh kalyan;Prakash Raj S | Admin Panel Bugs;Re-Opened Bugs;Major
Bug_Creator_Home_BUG_035_Numbers and special characters accepts in work link field | Gayathri Bandhila | User Panel Bugs;Minor;Verified Bugs
Bug-Signup_Bug-025Verify Send a Verification code is not clickable withouit entering the Email phone and Password | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S;Sandeep Reddy Bakkachennaiahgari | User Panel Bugs;Minor;Verified Bugs
Bug_Admin_Dashboard_BUG_018_project data is not there in te active projects | Gayathri Bandhila | Admin Panel Bugs;Minor;Verified Bugs
BUG_UserPanel_Myprofile page- Unable to add Skills | Sarvanaraj P;Jagadeesh kalyan;Prakash Raj S;Vijay Kumar N | User Panel Bugs;Verified Bugs
Suggestion_User panel (Creator)_Cancelled spelling | Sarvanaraj P;Barath Kaileash G.V;Prakash Raj S | Suggestion
BUG_User panel_My project_BUG_015_If the collaborator make the contract in pending its not reflected in creator section | Sarvanaraj P;Barath Kaileash G.V;Prakash Raj S | User Panel Bugs;New Bugs;Major
Bug_ Collaborator My Profile _Bug 51_ System has display as phone or phone verification, email has display as email or verification | Sarvanaraj P;ayyappa tellamekala;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;New Bugs;Minor
Bug_Login-Bug-029-Verify the availability of the “Forgot Password” option on the Login page | Sarvanaraj P;Mahesh Reddy Paduru;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;Verified Bugs;Major
Bug_Admin Subscription_BUG_004_The Plan Limits sub modules accepts only numeric Valves and rejects any Special characters | Aravind Sunkara;Sarvanaraj P;Prakash Raj S;Nala Sravan Kumar | Admin Panel Bugs;Minor;Verified Bugs
BUG_Admin panel_User_BUG_006_Status | Barath Kaileash G.V | Admin Panel Bugs;Verified Bugs
Bug-Beforesignup-Bug-004_Continue with Terms of Use not redirecting to Respective Page | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
Bug_Creator_Home_BUG_020_OTP is not receiving to email | Gayathri Bandhila | User Panel Bugs;Minor;Verified Bugs
Bug_Creator_Home_BUG_031_Country field accepts numbers and special characters | Gayathri Bandhila | User Panel Bugs;Minor;Verified Bugs
Bug_ Collaborator My Profile _Bug 55_ Verify email verification accepts only registered email | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;New Bugs;Minor
Bug_ Creator My Profile _Bug_017_ Pop-up message not displayed properly | Sarvanaraj P;ayyappa tellamekala;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;Re-Opened Bugs;Minor
Smoke Test Build version : 1.1.0_Admin Login & Notifications | Mahesh Reddy Paduru
Bug_Creator_Home_BUG_004_Delete option is not working in all jobs | Gayathri Bandhila | User Panel Bugs;Minor;Verified Bugs
BUG_UserPanel_Homepage - Skills not showing when searching the job | Sarvanaraj P;Prakash Raj S;Vijay Kumar N | User Panel Bugs;Verified Bugs
Bug_ Collaborator My Profile _Bug 47_ After clicking the mark all read button, the unread notification not move to read. | Sarvanaraj P;ayyappa tellamekala;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
Bug_ Collaborator My Profile _Bug_012_ System did not shows Error message " Please fill out this field | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Kolimi Shaik Fazil | User Panel Bugs;Minor;Verified Bugs
BUG_Admin Panel_User_BUG_007_Export Button | Barath Kaileash G.V | Verified Bugs
Bug_Creator-Subscription_BUG_002_The Subscribe to base plan button is not working in annual plan | Sarvanaraj P;Kolimi Shaik Fazil;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;Major;Verified Bugs
BUG_Creator_My project_All contract_Active contracts_BUG_003_Awaiting option is not working | Sarvanaraj P;Barath Kaileash G.V;Prakash Raj S;Deepak Rajan | User Panel Bugs;Verified Bugs
Bug_Creator-Subscription_BUG_009_The pricing unit for basic plan | Sarvanaraj P;Kolimi Shaik Fazil;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;Verified Bugs;Major
Suggestion_User panel (Creator)_The phone number should be static and we can have an edit button to edit the phone number and we can verify the phone number | Sarvanaraj P;Barath Kaileash G.V;Prakash Raj S | Suggestion
Bug_Financials_Withdraw_BUG_007_The Amount field accepts only numeric valves and rejects any alphabetic input. | Aravind Sunkara;Sarvanaraj P;Prakash Raj S;Deepak Rajan | User Panel Bugs;Re-Opened Bugs;Major
Bug_Creator_Home_BUG_033_In work field numbers and special characters are accepting for add portfolio | Gayathri Bandhila | User Panel Bugs;Minor;Verified Bugs
BUG_Admin panel_ User_ BUG_003_Suspended field | Barath Kaileash G.V | Verified Bugs
Bug-signup -Bug-031-Verify that the signup page should not accept non-Gmail email IDs. | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S;Sandeep Reddy Bakkachennaiahgari | User Panel Bugs;Verified Bugs;Major
Suggestion_UserPanel_HomePage- Job Activity list in Job description are not that much necessary for that section | Sarvanaraj P;Prakash Raj S;Vijay Kumar N | Suggestion
Bug_Financials_Withdraw_BUG_008_The Name field accepts only alphabetic characters and rejects any Special characters | Aravind Sunkara;Sarvanaraj P;Prakash Raj S;Deepak Rajan | User Panel Bugs;Re-Opened Bugs;Major
Smoke Test_Build Version: 1.0.4_Admin_Option | Barath Kaileash G.V | Smoke Test
Bug_Admin Subscription_BUG_006_The Download invoice Icon is not working properly. | Aravind Sunkara;Sarvanaraj P;Prakash Raj S;Nala Sravan Kumar | Admin Panel Bugs;Minor;Verified Bugs
BUG_User panel_Financials_BUG_003_Back button is not working in the stripe | Sarvanaraj P;Barath Kaileash G.V;Prakash Raj S;Deepak Rajan | User Panel Bugs;Re-Opened Bugs;Minor
Bug_Admin_Dashboard_BUG_009_Metric is not working in project status | Sarvanaraj P;Gayathri Bandhila;Prakash Raj S;Deepak Rajan | Admin Panel Bugs;Minor;Verified Bugs
Bug Subscription-Collaborator Page_BUG_006_ The Cardholder Name field length validation | Aravind Sunkara;Sarvanaraj P;Prakash Raj S | User Panel Bugs;New Bugs;Critical
Smoke Test_Build Version:1.0.1_SignUp and Login | Mahesh Reddy Paduru | Smoke Test
Suggestion_AdminPanel_Settings_Location denied pop up should not show every time we land | Sarvanaraj P;Prakash Raj S;Vijay Kumar N | Suggestion
Bug-Beforesignup-Bug-011 - Verify visibility of Terms & Services”, “Privacy Policy”, and “Cookies links on Before Signup page at 100% zoom | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S;Sandeep Reddy Bakkachennaiahgari | User Panel Bugs;Re-Opened Bugs;Major
BUG_UserPanel_MyWork- Back button is not working in All Contracts | Sarvanaraj P;Prakash Raj S;Deepak Rajan;Vijay Kumar N | User Panel Bugs;Verified Bugs
Smoke Test_Build Version:1.0.3_Collabortor Subscription and Financials | Aravind Sunkara | Smoke Test
Bug_ Collaborator My Profile _Bug_002_ The collaborator type is not displayed after clicking save button | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Minor;Verified Bugs
Suggestion_UserPanel_Homepage - Verified status should show only after verified | Sarvanaraj P;Prakash Raj S;Vijay Kumar N | Suggestion;Verified Bugs
Bug-Homepage -Bug-006While Clicking on Video Editor Functionality Not redirecting to editor page | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | User Panel Bugs;Re-Opened Bugs;Verified Bugs
Bug_ Collaborator My Profile _Bug_035_ After entering Invalid numbers, special characters, alphabets in the all fields are saved without any error message | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Verified Bugs;Major
Bug_ Collaborator My Profile _Bug 52_ Availability and collaboration type fields has accept special character “-” (hyphen) | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Nala Sravan Kumar | User Panel Bugs;Minor;Verified Bugs
Bug_Creator_Home_BUG_027_Profile picture is not displaying in complete profile | Sarvanaraj P;Gayathri Bandhila;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
BUG_UserPanel_Home_page- Cancelled projects | Prakash Raj S;Deepak Rajan;Vijay Kumar N | User Panel Bugs;Verified Bugs
Bug Subscription-Collaborator Page_BUG_005_ The cardholder name field accepts Special characters. | Aravind Sunkara;Sarvanaraj P;Prakash Raj S | User Panel Bugs;New Bugs;Critical
Bug_ Collaborator My Profile _Bug_028_ Pop-up message not displayed after saving | Sarvanaraj P;ayyappa tellamekala;Prakash Raj S;Deepak Rajan | User Panel Bugs;Minor;Verified Bugs
Task_001-Test Join as Creator Profile Page | Gayathri Bandhila | Task
Smoke Test_ Build Version:1.0.1_Creator Subscription and Creator and Collaborator My Profile, Message & Notification | ayyappa tellamekala | User Panel Bugs;Smoke Test
Bug_Admin_Dashboard_BUG_020_Delivered data is not there in active projects | Gayathri Bandhila | Admin Panel Bugs;Minor;Verified Bugs
Bug-Homepage -Bug-013-Verify Click on Create Your profile | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S;Akash Barik | User Panel Bugs;Minor;Verified Bugs
Bug-Beforesignup- Verify clicking on Google Coount | Mahesh Reddy Paduru | User Panel Bugs;Minor;Verified Bugs
BUG_Creator_My project_BUG_004_Active contract_Message window is not working | Sarvanaraj P;Barath Kaileash G.V;Jagadeesh kalyan;Prakash Raj S | User Panel Bugs;Verified Bugs
BUG Test Collaborator Home page Functionalities - Subscription button | Vijay Kumar N | User Panel Bugs;Major
Bug_Creator_ Find Collaborator_Collaborate request page _BUG_005_Back button is not there in the collaborate request page | Sarvanaraj P;Gayathri Bandhila;Prakash Raj S;Nala Sravan Kumar | User Panel Bugs;Minor;Verified Bugs
Bug_Creator-Subscription_BUG_008_The Back button is not working properly in Agent plan | Sarvanaraj P;Kolimi Shaik Fazil;ayyappa tellamekala;Prakash Raj S | User Panel Bugs;Minor;Verified Bugs
Suggestion_User panel (Creator)_We can able to have a drop down list which carries the job title by that the creator can select the join for the collaborator | Sarvanaraj P;Barath Kaileash G.V;Prakash Raj S | Suggestion
BUG_UserPanel_MyWorks - After cancelling a job, it is not reflecting in All jobs | Sarvanaraj P;Prakash Raj S;Vijay Kumar N | User Panel Bugs;New Bugs;Major
Smoke Test Build version : 1.0.1_Admin Login & Notifications | Mahesh Reddy Paduru | Smoke Test
Smoke Test_Build Version:1.0.1_Creator Profile, Home and Find Collaborator | Gayathri Bandhila | User Panel Bugs;Smoke Test
BUG_Admin panel_User_BUG_018_missing some information in Exported data | Sarvanaraj P;Barath Kaileash G.V;Prakash Raj S | Admin Panel Bugs;Verified Bugs
Smoke Test_Build Version: 1.0.4_Admin_User | Barath Kaileash G.V | Smoke Test
BUG_Creator_My project_All contract_Active contract_BUG_001_All option not working | Sarvanaraj P;Barath Kaileash G.V;Prakash Raj S;Deepak Rajan | User Panel Bugs;Verified Bugs
Task_002-Test Financials - Overview Functionalities | Aravind Sunkara | Task
Bug_Homepage _Bug-024_Description of the top skill category shows diffrent Language | Sarvanaraj P;Mahesh Reddy Paduru;Prakash Raj S | User Panel Bugs;Verified Bugs;Major
Bug_Admin Subscription_BUG_009_System should not display duplicate records in the list or table. | Aravind Sunkara;Sarvanaraj P;Prakash Raj S | Admin Panel Bugs;New Bugs;Major
Task_003-Test My Work- All Contracts Fucntionalities | Vijay Kumar N | Task
Task_001-Test Before Sign-In functionalities | Mahesh Reddy Paduru | Task
Task_005-Test Financials -Wallet overview functionalities | Barath Kaileash G.V | Task
Smoke Test_Build Version:1.0.1_Join as a creator, my project & Financials | Barath Kaileash G.V | User Panel Bugs;Smoke Test
BUG_User panel_Financials_BUG_006_Payment is not processed to stripe | Sarvanaraj P;Barath Kaileash G.V;Prakash Raj S;Deepak Rajan | User Panel Bugs;Re-Opened Bugs;Major
Suggestion_User panel(Creator)_Cant able to click and look the prolife detail from the creator home page | Sarvanaraj P;Barath Kaileash G.V;Prakash Raj S | Suggestion
BUG_Landing Page_BUG_001_Font size is bigger in the wqebpage | Sarvanaraj P;Barath Kaileash G.V;Prakash Raj S | New Bugs
BUG_Admin_Settings_page-Password is changing even if we give existing password | Sarvanaraj P;Prakash Raj S;Vijay Kumar N | Admin Panel Bugs;Verified Bugs

## Plan name
Plan name | CCW
Plan ID | wBTOpTI8VEuccHEhmCFJs-EAGV1Z
Date of export | 05/15/2026